## ProjectSchedule
Thapar Trade
UCS503P - Software Engineering Lab, Thapar Institute |  | Project Start: | 2026-08-03
Team: Rajbir, Chitesh Jindal, Ishan Garg |  | Today: | 2026-09-14
|  | Display Week: | 1
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS
Phase 1: Project Proposal & Research
Project scope and requirement planning | All | 100% | 2026-08-03 | 2026-08-09
Problem statement and marketplace scope | Rajbir | 100% | 2026-08-10 | 2026-08-16
Project documentation setup | Rajbir | 100% | 2026-08-17 | 2026-08-20
Software Engineering presentation | Ishan | 100% | 2026-08-17 | 2026-08-23
Requirements review and feedback | All | 100% | 2026-08-21 | 2026-08-23
Phase 2: System Design & Modeling
Define users and marketplace workflows | All | 100% | 2026-08-24 | 2026-08-30
UML use case and class diagrams | Rajbir | 100% | 2026-08-24 | 2026-09-06
DFD and UML sequence diagrams | Chitesh | 100% | 2026-08-24 | 2026-09-13
Project journal and documentation | Ishan | 100% | 2026-08-30 | 2026-09-06
Consolidate project report | Ishan | 100% | 2026-08-30 | 2026-09-06
Phase 3: Frontend Design & Planning
Marketplace data and listing model | Rajbir | 100% | 2026-09-07 | 2026-09-08
GitHub Pages setup and prototype documentation | Rajbir | 100% | 2026-09-07 | 2026-09-13
Plan listing and user interaction flow | Rajbir | 100% | 2026-09-08 | 2026-09-10
Define listing moderation and reporting flow | Chitesh | 100% | 2026-09-09 | 2026-09-10
Review project metrics and remaining work | All | 40% | 2026-09-11 | 2026-10-04
Phase 4: Implementation - Core Marketplace
Implement marketplace listing workflow | Rajbir | 100% | 2026-09-09 | 2026-09-13
Implement listing validation and user flow | Chitesh | 100% | 2026-09-10 | 2026-09-13
Implement browse and listing display | Ishan | 100% | 2026-09-10 | 2026-09-13
Cart and order flow review | All | 0% | 2026-10-26 | 2026-11-01
Frontend testing and bug fixes | Ishan | 60% | 2026-09-11 | 2026-11-08
Phase 5: Testing & Final Submission
Review listing reports and moderation flow | Chitesh | 100% | 2026-09-10 | 2026-09-13
End-to-end testing | All | 30% | 2026-09-11 | 2026-11-22
Final report and documentation | Rajbir | 0% | 2026-11-16 | 2026-11-22
Final presentation preparation | All | 0% | 2026-11-23 | 2026-11-29
Project submission and demo | All | 0% | 2026-11-30 | 2026-12-04
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template is adapted for the Thapar Trade campus marketplace project. Task dates and progress are copied from the Deadstock Management System schedule as requested.
Project team: Rajbir, Chitesh Jindal, Ishan Garg.
Project activities: requirements, UML diagrams, React frontend, testing, journal, GitHub Pages, presentation, and final report.
Dates and progress values match the corresponding rows in the Deadstock Management System schedule.
Task assignments are allocated to the listed Thapar Trade team members.
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.